

**GEOPHYSICS SECTION WEEKLY REPORT**

**Period:** Sep 5th 2022– Sep 9th 2022

| **GEOPHYSICS SECTION** | | | | | |
| --- | --- | --- | --- | --- | --- |
|  | **On-going Activities** | **Planned** | | **Actual in % completion** | **Status** |
| **Start Date** | **End Date** |  |  |
|  | Trade in of old MTU-5A to MTU-5C | 15/8/2022 | 30/11/2022 | 10% | * Ongoing(Working on the draft paper.) |
|  | Following on payment of the spares and electrodes to phoenix. | 11/7/2022 | 31/09/2022 | 80% | * Ongoing.(waiting for dispatch by the clearing agent) |
|  | Reviewing GAB report recommendations. | 4/7/2022 | 29/9/2022 | Ongoing | * Ongoing |
|  | New Procurement document for tender for supply of scientific equipment and accessories for Geophysics | 04/6/2022 | 30/9/2022 | 10% | * Raising a PR and restarting the process. |
|  | Reviewing Korosi well sites | 15/8/2022 | 30/9/2022 | ongoing | * ongoing |
|  | Working on specifications for geophysics laboratories in kabarak. | 14/7/2022 | 31/12/2022 | 10% | * Ongoing |
|  | -Inception report for Korosi, paka ,suswa and Menengai field. | 11/7/2022 | 30/9/2022 | Ongoing | * Ongoing |
|  | Equipment maintenance and repair | 18/7/2022 | 30/9/2022 | 80% | * Ongoing |
|  | Seismics data reprocessing using seisan software. | 03/01/2022 | 31/12/2022 | 70% | * ongoing |
|  | GDC –JRG Geo science workshop | 26/5/2022 | 31/12/2022 | ongoing | * ongoing |
|  | Capacity building on 24 bit GDP and 24 bit transmitter, MTU-5C, EM power software and SYSCAL for ground water measurement | 15/8/2022 | 30/11/2022 | 10% | * Ongoing |
|  | -GCE consultancy meetings | 25/7/2022 | 30/9/2022 | ongoing | * ongoing |
|  | Micro-seismics data recording for geohazard monitoring in Paka /Korosi prospect. | 03/01/2022 | 31/12/2022 | Ongoing | * ongoing |
|  | Seismics network design software testing for menengai prospect. | 25/7/2022 | ongoing | 50% | * ongoing |
|  | Participation in ISO internal audit | 6/9/2022 | 6/9/2022 | 100% | * Done |